## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | E-fresh : Computer Vision and IOT Framework for fruit freshness detection |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP Shah Institute of Technology, IT Department
PROJECT GUIDE |  | Prof. Kiran Deshpande |  |  |  |  | DATE | [6 empty] | 2022-04-08
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2021-07-10 | 2021-07-26 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Research paper finalization | Akshata Gawas, Krishita Tolia, Siddhesh Gaikwad | 2021-07-10 | 2021-07-26 | 3 | 100% | bar: WEEK 2 W
1.2 | Project Title | Krishita Tolia, Siddhesh Gaikwad, Akshata Gawas | 2021-07-10 | 2021-07-26 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Abstract | Siddhesh Gaikwad | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Objectives | Krishita Tolia | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Literature Review | Akshata Gawas | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Problem Definition | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2021-03-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 F
1.7 | Scope | Krishita Tolia | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 F
1.8 | Technology stack | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 F
1.9 | Benefits for environment | Siddhesh Gaikwad, Krishita Tolia | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 F
1.1 | Benefits for society | Siddhesh Gaikwad, Akshata Gawas | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 F
1.11 | Applications | Krishita Tolia, Akshata Gawas | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 F
2 | Project Design
2.1 | Proposed System | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2021-09-19 | 2021-09-27 | 1 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2021-09-19 | 2021-09-27 | 1 | 100% | bar: WEEK 4 F to WEEK 5 F
2.3 | Activity Diagram | Siddhesh Gaikwad, Krishita Tolia | 2021-09-19 | 2021-09-27 | 1 | 100%
2.4 | Use Case Diagram | Siddhesh Gaikwad | 2021-09-19 | 2021-09-27 | 1 | 100%
2.5 | Description Of Use Case | Akshata Gawas | 2021-09-19 | 2021-09-27 | 1 | 100%
2.6 | Hardware Architecture | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2021-09-19 | 2021-09-27 | 1 | 100%
2.7 | Software Architecture | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2021-09-19 | 2021-09-27 | 1 | 100%
3 | Project Implementation
3.1 | Dataset Creation | Siddhesh Gaikwad | 2021-10-01 | 2021-12-25 | 3 | 100%
3.2 | Image Classification | Siddhesh Gaikwad | 2021-10-01 | 2021-12-25 | 3 | 100%
3.3 | Mq3 Sensor Reading | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2021-10-01 | 2021-12-25 | 3 | 100%
3.4 | Mq4 Sensor Reading | Krishita Tolia | 2021-10-01 | 2021-12-25 | 3 | 100%
3.5 | Dashboard Visualisation | Akshata Gawas | 2021-10-01 | 2021-12-25 | 3 | 100%
4 | Testing
4.1 | Design of Test Cases | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2022-01-07 | 2022-01-24 | 3 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 T to WEEK 2 F; WEEK 3 T to WEEK 3 F
4.2 | Image Classification | Akshata Gawas | 2022-01-27 | 2022-02-03 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.3 | Mq3 Sensor | Siddhesh Gaikwad | 2022-02-04 | 2022-02-10 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.4 | Mq4 Sensor | Krishita Tolia | 2022-02-11 | 2022-02-17 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.5 | Unit Testing | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2022-02-18 | 2022-02-24 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.6 | Automation | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2022-02-25 | 2022-03-02 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
5 | Report Preparation
5.1 | Black Book | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2022-03-01 | 2022-04-01 | 1 | 100%
5.2 | PPT | Siddhesh Gaikwad, Krishita Tolia, Akshata Gawas | 2022-03-01 | 2022-04-01 | 1 | 100%
5.3 | Gantt Chart | Siddhesh Gaikwad | 2022-03-01 | 2022-04-01 | 1 | 100% | bar: WEEK 12 M to WEEK 12 F