## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Automation of Supply Chain Management for Healthcare |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A. P. Shah Institute of Technology
PROJECT GUIDE |  | Prof. Vishal Badgujar |  |  |  |  | DATE | [6 empty] | 2022-07-04
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Jash, Hitarth, Samyak | 2021-02-08 | 2021-02-12 | 1 | 100% | bar: WEEK 1 M to WEEK 1 R; WEEK 2 M to WEEK 2 W; WEEK 5 W to WEEK 5 R
1.1.1 | Research paper finalization | Jash, Hitarth, Samyak | 2021-02-11 | 2021-02-12 | 1 | 100% | bar: WEEK 1 R to WEEK 1 F; WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R
1.2 | Project Title | Jash, Hitarth, Samyak | 2021-05-10 | 2021-05-11 | 1 | 100% | bar: WEEK 5 W to WEEK 5 R
1.3 | Abstract | Jash | 2021-05-10 | 2021-05-11 | 1 | 100% | bar: WEEK 5 W to WEEK 5 R
1.4 | Objectives | Hitarth | 2021-05-10 | 2021-05-11 | 1 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 5 W to WEEK 5 R
1.5 | Literature Review | Samyak | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R
1.6 | Problem Definition | Jash | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R
1.7 | Scope | Hitarth | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R
1.8 | Technology stack | Jash, Hitarth, Samyak | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 W to WEEK 5 R
1.9 | Benefits for environment | Samyak | 2021-05-13 | 2021-05-14 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 W to WEEK 5 R
1.1 | Benefits for society | Samyak | 2021-05-13 | 2021-05-14 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 W to WEEK 5 R
1.11 | Applications | Jash, Hitarth | 2021-05-13 | 2021-05-14 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 W to WEEK 5 R
2 | Project Design
2.1 | Proposed System | Hitarth, Jash, Samyak | 2021-06-14 | 2021-06-15 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 3 M to WEEK 3 T; WEEK 5 W to WEEK 5 R
2.2 | Design(Flow Of Modules) | Jash | 2021-06-14 | 2021-06-16 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 3 M to WEEK 3 T
2.3 | Activity Diagram | Hitarth | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 3 W to WEEK 3 F; WEEK 5 W to WEEK 5 R
2.4 | Use Case Diagram | Samyak | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 3 W to WEEK 3 F; WEEK 5 W to WEEK 5 R
2.5 | Description Of Use Case | Samyak | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 3 R to WEEK 3 F; WEEK 5 W to WEEK 5 R
2.6 | Database Design | Jash | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 3 R to WEEK 3 F; WEEK 5 W to WEEK 5 R
2.6.1 | Distributor Table Design | Hitarth | 2021-06-21 | 2021-06-23 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 4 M to WEEK 4 T; WEEK 5 W to WEEK 5 R
2.6.2 | Inventory Table Design | Samyak | 2021-06-22 | 2021-06-23 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 4 M to WEEK 4 T; WEEK 5 W to WEEK 5 R
2.6.3 | Potential Distributor Table Design | Samyak | 2021-06-21 | 2021-06-23 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 4 M to WEEK 4 W; WEEK 5 W to WEEK 5 R
2.6.4 | Quotation Table Design | Hitarth | 2021-06-22 | 2021-06-24 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 4 M to WEEK 4 W; WEEK 5 W to WEEK 5 R
2.7 | Preparation Of Report | Hitarth, Samyak, Jash | 2021-06-23 | 2021-06-25 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 4 T to WEEK 4 F; WEEK 5 W to WEEK 5 R
3 | Project Implementation
3.1 | Inventory Management | Jash | 2021-07-05 | 2021-08-05 | 4 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 M to WEEK 8 F
3.2 | Vendor Onboarding | Hitarth | 2021-07-05 | 2021-08-05 | 4 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 M to WEEK 8 F
3.3 | Vendor Selection | Samyak | 2021-07-05 | 2021-08-05 | 4 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 M to WEEK 8 F
3.4 | Order Processing | Jash, Hitarth, Samyak | 2021-07-05 | 2021-08-05 | 4 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 M to WEEK 8 F
3.5 | Integration of frontend to BluePrism |  |  |  | 0 | 0% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 M to WEEK 8 F
4 | Testing
4.1 | Design of Test Cases | Jash, Hitarth, Samyak | 2021-07-06 | 2021-07-09 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 T to WEEK 5 R
4.2 | Product-Reordering module test | Samyak | 2021-07-07 | 2021-07-09 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R
4.3 | Order-Received module test | Jash | 2021-07-07 | 2021-07-09 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R
4.4 | Creating-Quotation-Template module test | Hitarth | 2021-07-10 | 2021-07-11 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 6 M
4.5 | Requesting-Quotation email test | Hitarth | 2021-07-11 | 2021-07-14 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 6 W
4.6 | Receiving-Quotation module test | Samyak | 2021-07-15 | 2021-07-16 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R; WEEK 6 R to WEEK 6 F
4.7 | Reading-ExcelQuotation module test | Jash | 2021-07-17 | 2021-07-19 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R; WEEK 7 M to WEEK 7 W
4.8 | Vendor-Selection code testing | Jash | 2021-07-20 | 2021-07-21 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R; WEEK 7 W to WEEK 7 F
4.9 | Vendor-Selection module testing | Samyak | 2021-07-22 | 2021-07-23 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R; WEEK 8 M to WEEK 8 T
4.1 | Vendor-Onboarding testing | Hitarth | 2021-07-24 | 2021-07-26 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R; WEEK 8 W to WEEK 8 F
5 Report Preparation
5.1 | Black Book | Samyak, Hitarth, Jash | 2021-07-27 | 2021-08-17 | 3 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 T to WEEK 5 R; WEEK 9 M to WEEK 11 F
5.2 | PPT | Samyak, Hitarth, Jash | 2021-08-10 | 2021-08-17 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R
5.3 | Gnatt Chart | Samyak, Hitarth, Jash | 2021-08-18 | 2021-08-24 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 W to WEEK 5 R; WEEK 12 M to WEEK 12 F