## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Annadata: A Web Based Farmer's Portal |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY -Information Technology
PROJECT GUIDE |  | Dr.Sameer Nanivadekar |  |  |  |  | DATE | [6 empty] | 2022-03-25
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Kaustubh,Swarad,Shubham | 2021-02-08 | 2021-02-12 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F; WEEK 2 W to WEEK 2 F
1.1.1 | Research paper finalization | Kaustubh,Swarad,Shubham | 2021-02-11 | 2021-02-12 | 1 | 100% | bar: WEEK 1 R to WEEK 2 T; WEEK 2 R to WEEK 2 F
1.2 | Project Title | Kaustubh,Swarad,Shubham | 2021-05-10 | 2021-05-11 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.3 | Abstract | Swarad | 2021-05-10 | 2021-05-11 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.4 | Objectives | Kaustubh | 2021-05-10 | 2021-05-11 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.5 | Literature Review | Kaustubh,Swarad,Shubham | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.6 | Problem Definition | Shubham | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.7 | Scope | Swarad | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.8 | Technology stack | Kaustubh | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.9 | Benefits for environment | Swarad,Shubham | 2021-05-13 | 2021-05-14 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F
1.1 | Benefits for society | Swarad,Shubham | 2021-05-13 | 2021-05-14 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F
1.11 | Applications | Swarad,Shubham | 2021-05-13 | 2021-05-14 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F
2 | Project Design
2.1 | Proposed System | Kaustubh | 2021-06-14 | 2021-06-15 | 1 | 100% | bar: WEEK 2 M to WEEK 3 T
2.2 | Design(Flow Of Modules) | Kaustubh,Shubham | 2021-06-14 | 2021-06-16 | 1 | 100% | bar: WEEK 2 M to WEEK 3 W
2.3 | Activity Diagram | Swarad,Shubham | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.4 | Use Case Diagram | Kaustubh | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.5 | Sequence Diagram | Swarad | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.6 | Description Of Use Case | Kaustubh | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.7 | Modules | Shubham | 2021-06-21 | 2021-06-23 | 1 | 100% | bar: WEEK 4 M to WEEK 4 W
2.7.1 | Application Module | Shubham,Swarad | 2021-06-22 | 2021-06-23 | 1 | 100% | bar: WEEK 4 T to WEEK 4 W
2.8 | Preparation Of Report | Kaustubh,Swarad,Shubham | 2021-06-23 | 2021-06-25 | 1 | 100% | bar: WEEK 4 W to WEEK 4 F
3 | Project Implementation
3.1 | Login,Registration | Shubham | 2021-07-05 | 2021-08-13 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
3.2 | Modules Implementation | Kaustubh | 2021-07-05 | 2021-08-13 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
4 | Testing
4.1 | Design of Test Cases | Kaustubh | 2021-07-05 | 2021-07-06 | 1 | 100% | bar: WEEK 2 M; WEEK 5 M to WEEK 5 T
4.2.1 | Login Page Unit testing | Shubham | 2021-07-06 | 2021-07-07 | 1 | 100% | bar: WEEK 5 T to WEEK 5 W
4.2.2 | Register Page Unit testing | Shubham | 2021-07-07 | 2021-07-08 | 1 | 100% | bar: WEEK 5 W to WEEK 5 R
4.2.3 | Home Page Unit testing | Kaustubh,Shubham | 2021-07-08 | 2021-07-09 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F
4.2.4 | Integration Testing of above pages | Kaustubh | 2021-07-08 | 2021-07-09 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F
4.2.5 | User Reset Password | Shubham | 2021-07-19 | 2021-07-21 | 1 | 100% | bar: WEEK 6 M to WEEK 6 W
4.2.6 | Registration SMS Testing | Kaustubh,Shubham | 2021-07-19 | 2021-07-21 | 1 | 100% | bar: WEEK 6 M to WEEK 6 W
4.2.7 | Weather Prediction | Shubham | 2021-07-21 | 2021-07-23 | 1 | 100% | bar: WEEK 6 W to WEEK 6 F
4.2.8 | Weather Red Flags SMS Testing | Kaustubh,Shubham | 2021-08-02 | 2021-08-03 | 1 | 100% | bar: WEEK 7 M to WEEK 7 T
4.2.9 | Government Schemes Backend | Kaustubh,Swarad | 2021-08-03 | 2021-08-04 | 1 | 100% | bar: WEEK 7 T to WEEK 7 R
4.2.10 | Government Schemes SMS Testing | Shubham | 2021-08-03 | 2021-08-05 | 1 | 100% | bar: WEEK 7 T to WEEK 7 R
4.3.1 | Crop Prediction Model | Kaustubh | 2021-08-04 | 2021-08-05 | 1 | 100% | bar: WEEK 7 W to WEEK 7 R
4.3.2 | Crop Prediction UI | Kaustubh | 2021-08-04 | 2021-08-06 | 1 | 100% | bar: WEEK 7 W to WEEK 7 F
4.3.3 | Crop Prediction-Will Plant Testing | Kaustubh | 2021-08-05 | 2021-08-06 | 1 | 100% | bar: WEEK 7 R to WEEK 7 F
4.3.4 | Crop Prediction Backend | Kaustubh | 2021-08-09 | 2021-08-10 | 1 | 100% | bar: WEEK 8 M to WEEK 8 T
4.3.5 | User List Backend | Kaustubh | 2021-08-09 | 2021-08-10 | 1 | 100% | bar: WEEK 8 M to WEEK 8 T
4.3.6 | Admin Page UI | Shubham | 2021-08-11 | 2021-08-12 | 1 | 100% | bar: WEEK 8 W to WEEK 8 R
4.3.7 | Soil and Water Conservation | Swarad,Shubham | 2021-08-11 | 2021-08-13 | 1 | 100% | bar: WEEK 8 W to WEEK 8 F
4.3.8 | Equipment Shop Backend | Kaustubh,Shubham | 2021-08-12 | 2021-08-13 | 1 | 100% | bar: WEEK 8 R to WEEK 8 F
5 | Report Preparation
5.1 | Black Book | Swarad | 2021-10-04 | 2021-10-08 | 1 | 100%
5.1 | PPT | Swarad | 2021-10-04 | 2021-10-08 | 1 | 100%
5.1 | Gantt Chart | Swarad | 2021-10-11 | 2021-10-15 | 1 | 100% | bar: WEEK 12 M to WEEK 12 F