## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | BeSafe: IoT Based Safety Band |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY
PROJECT GUIDE |  | Prof. Anagha Aher |  |  |  |  | DATE | [6 empty] | 2022-03-25
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Ganesh, Krishi, Riddhi | 2021-02-08 | 2021-02-12 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F
1.1.1 | Research paper finalization | Ganesh, Krishi, Riddhi | 2021-02-11 | 2021-02-12 | 1 | 100% | bar: WEEK 1 R to WEEK 1 F
1.2 | Project Title | Ganesh, Krishi, Riddhi | 2021-05-10 | 2021-05-11 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.3 | Abstract | Riddhi | 2021-05-10 | 2021-05-11 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.4 | Objectives | Krishi | 2021-05-10 | 2021-05-11 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.5 | Literature Review | Ganesh, Krishi, Riddhi | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.6 | Problem Definition | Krishi | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.7 | Scope | Krishi | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.8 | Technology stack | Ganesh | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.9 | Benefits for environment | Ganesh, Krishi, Riddhi | 2021-05-13 | 2021-05-14 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F
1.1 | Benefits for society | Ganesh, Krishi, Riddhi | 2021-05-13 | 2021-05-14 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F
1.11 | Applications | Ganesh, Krishi, Riddhi | 2021-05-13 | 2021-05-14 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F
2 | Project Design
2.1 | Proposed System | Ganesh | 2021-06-14 | 2021-06-15 | 1 | 100% | bar: WEEK 3 M to WEEK 3 T
2.2 | Design(Flow Of Modules) | Ganesh | 2021-06-14 | 2021-06-16 | 1 | 100% | bar: WEEK 3 M to WEEK 3 W
2.3 | Activity Diagram | Ganesh | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.4 | Use Case Diagram | Ganesh | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.5 | Sequence Diagram | Ganesh | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.6 | Description Of Use Case | Ganesh | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.7 | Modules | Ganesh | 2021-06-21 | 2021-06-23 | 1 | 100% | bar: WEEK 4 M to WEEK 4 W
2.7.1 | Application Module | Ganesh | 2021-06-22 | 2021-06-23 | 1 | 100% | bar: WEEK 4 T to WEEK 4 W
2.7.2 | Hardware Module | Krishi, Riddhi | 2021-06-21 | 2021-06-23 | 1 | 100% | bar: WEEK 4 M to WEEK 4 W
2.7.3 | App & Hardware Module | Krishi, Riddhi | 2021-06-22 | 2021-06-24 | 1 | 100% | bar: WEEK 4 T to WEEK 4 R
2.8 | Preparation Of Report | Ganesh, Krishi, Riddhi | 2021-06-23 | 2021-06-25 | 1 | 100% | bar: WEEK 4 W to WEEK 4 F
3 | Project Implementation
3.1 | Application Implementation | Ganesh | 2021-07-05 | 2021-08-13 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
3.2 | Hardware Implementation | Krishi, Riddhi | 2021-07-05 | 2021-08-13 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
3.3 | App & Hardware Integration | Ganesh, Krishi, Riddhi | 2021-09-13 | 2021-09-24 | 2 | 10% | bar: WEEK 9 M to WEEK 10 F
4 | Testing
4.1 | Design of Test Cases | Ganesh | 2021-07-05 | 2021-07-06 | 1 | 100% | bar: WEEK 5 M to WEEK 5 T
4.2.1 | Login Page Unit testing | Ganesh | 2021-07-06 | 2021-07-07 | 1 | 100% | bar: WEEK 5 T to WEEK 5 W
4.2.2 | Register Page Unit testing | Ganesh | 2021-07-07 | 2021-07-08 | 1 | 100% | bar: WEEK 5 W to WEEK 5 R
4.2.3 | Home Page Unit testing | Ganesh | 2021-07-08 | 2021-07-09 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F
4.2.4 | Integration Testing of above pages | Ganesh | 2021-07-08 | 2021-07-09 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F
4.2.5 | Location Tracking Unit testing | Ganesh | 2021-07-19 | 2021-07-21 | 1 | 100% | bar: WEEK 6 M to WEEK 6 W
4.2.6 | Message Service Unit Testing | Ganesh | 2021-07-19 | 2021-07-21 | 1 | 100% | bar: WEEK 6 M to WEEK 6 W
4.2.7 | Integration Testing of both Functions | Ganesh | 2021-07-21 | 2021-07-23 | 1 | 100% | bar: WEEK 6 W to WEEK 6 F
4.2.8 | SOS button Integration Testing | Ganesh | 2021-08-02 | 2021-08-03 | 1 | 100% | bar: WEEK 7 M to WEEK 7 T
4.2.9 | Emergency Call Unit Testing | Ganesh | 2021-08-03 | 2021-08-04 | 1 | 100% | bar: WEEK 7 T to WEEK 7 R
4.2.10 | Safe Places Unit Testing | Ganesh | 2021-08-03 | 2021-08-05 | 1 | 100% | bar: WEEK 7 T to WEEK 7 R
4.3.1 | Contacts Page Unit Testing | Ganesh | 2021-08-04 | 2021-08-05 | 1 | 100% | bar: WEEK 7 W to WEEK 7 R
4.3.2 | Contacts DB Helper Unit Testing | Ganesh | 2021-08-04 | 2021-08-06 | 1 | 100% | bar: WEEK 7 W to WEEK 7 F
4.3.3 | Integration of Contacts with SOS | Ganesh | 2021-08-05 | 2021-08-06 | 1 | 100% | bar: WEEK 7 R to WEEK 7 F
4.3.4 | Location Updating in Firestore Unit Testing | Ganesh | 2021-08-09 | 2021-08-10 | 1 | 100% | bar: WEEK 8 M to WEEK 8 T
4.3.5 | Settings Page Unit Testing | Ganesh | 2021-08-09 | 2021-08-10 | 1 | 100% | bar: WEEK 8 M to WEEK 8 T
4.3.6 | Analysis Page Unit Testing | Ganesh | 2021-08-11 | 2021-08-12 | 1 | 100% | bar: WEEK 8 W to WEEK 8 R
4.3.7 | Bluetooth Unit Testing | Ganesh | 2021-08-11 | 2021-08-13 | 1 | 100% | bar: WEEK 8 W to WEEK 8 F
4.3.8 | Compatibility Testing in other OS | Ganesh | 2021-08-12 | 2021-08-13 | 1 | 100% | bar: WEEK 8 R to WEEK 8 F
4.4 | Hardware Components Testng | Krishi, Riddhi | 2021-07-05 | 2021-07-09 | 1 | 100%
4.5 | Connectivity Testing between Components | Krishi, Riddhi | 2021-07-19 | 2021-07-23 | 1 | 100% | bar: WEEK 6 M to WEEK 6 F
4.6 | Circuit Testing | Krishi, Riddhi | 2021-08-02 | 2021-08-06 | 1 | 100% | bar: WEEK 7 M to WEEK 7 F
4.7 | Hardware Code Testing | Krishi, Riddhi | 2021-08-09 | 2021-08-13 | 1 | 100%
4.8 | Bluetooth Connection | Ganesh | 2021-09-13 | 2021-09-17 | 1 | 100% | bar: WEEK 9 M to WEEK 9 F
5 | Report Preparation
5.1 | Black Book | Ganesh | 2021-10-04 | 2021-10-08 | 1 | 100%
5.1 | PPT | Ganesh, Krishi, Riddhi | 2021-10-04 | 2021-10-08 | 1 | 100%
5.1 | Gantt Chart | Ganesh | 2021-10-11 | 2021-10-15 | 1 | 100% | bar: WEEK 12 M to WEEK 12 F