## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Using AI for Designing ID Cards Embedded with Invisible QR Code |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A P SHAH INSTITUTE OF TECHNOLOGY
PROJECT GUIDE |  | Prof. Kiran Deshpande |  |  |  |  | DATE | [6 empty] | 2022-04-07
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Dhruva, Chirag | 2021-02-08 | 2021-02-12 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F; WEEK 2 W to WEEK 2 F
1.1.1 | Research paper finalization | Dhruva, Chirag, Prem | 2021-02-11 | 2021-02-12 | 1 | 100% | bar: WEEK 1 R to WEEK 2 T; WEEK 2 R to WEEK 2 F
1.2 | Project Title | Dhruva, Chirag, Prem | 2021-05-10 | 2021-05-11 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.3 | Abstract | Dhruva | 2021-05-10 | 2021-05-11 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.4 | Objectives | Prem | 2021-05-10 | 2021-05-11 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.5 | Literature Review | Dhruva, Chirag | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.6 | Problem Definition | Chirag | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.7 | Scope | Prem | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.8 | Technology stack | Chirag, Dhruva | 2021-05-12 | 2021-05-13 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.9 | Benefits for environment | Chirag, Dhruva | 2021-05-13 | 2021-05-14 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F
1.1 | Benefits for society | Dhruva | 2021-05-13 | 2021-05-14 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F
1.11 | Applications | Chirag | 2021-05-13 | 2021-05-14 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F
2 | Project Design
2.1 | Proposed System | Dhruva | 2021-06-14 | 2021-06-15 | 1 | 100% | bar: WEEK 2 M to WEEK 3 T
2.2 | Design(Flow Of Modules) | Chirag | 2021-06-14 | 2021-06-16 | 1 | 100% | bar: WEEK 2 M to WEEK 3 W
2.3 | Activity Diagram | Dhruva | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.4 | Use Case Diagram | Prem | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.5 | Sequence Diagram | Dhruva | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.6 | Description Of Use Case | Chirag | 2021-06-16 | 2021-06-18 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.7 | Modules | Dhruva | 2021-06-21 | 2021-06-23 | 1 | 100% | bar: WEEK 4 M to WEEK 4 W
2.7.1 | Application Module | Dhruva | 2021-06-22 | 2021-06-23 | 1 | 100% | bar: WEEK 4 T to WEEK 4 W
2.7.2 | App & Hardware Module | Chirag, Dhruva | 2021-06-22 | 2021-06-24 | 1 | 100% | bar: WEEK 4 T to WEEK 4 R
2.8 | Preparation Of Report | Dhruva, Chirag, Prem | 2021-06-23 | 2021-06-25 | 1 | 100% | bar: WEEK 4 W to WEEK 4 F
3 | Project Implementation
3.1 | Application Implementation | Chirag, Dhruva | 2021-07-05 | 2021-08-13 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
4 | Testing
4.1 | Design of Test Cases | Dhruva | 2021-10-05 | 2022-11-02 | 4 | 100% | bar: WEEK 2 M; WEEK 5 M to WEEK 5 T
4.2.1 | QR generator testing | Dhruva | 2021-10-06 | 2022-11-07 | 4 | 100% | bar: WEEK 5 T to WEEK 5 W
4.2.2 | CNN encoder model testing | Chirag | 2021-11-07 | 2022-01-08 | 6 | 100% | bar: WEEK 5 W to WEEK 5 R
4.2.3 | CNN decoder model testing | Chirag | 2022-01-10 | 2022-02-12 | 4 | 100% | bar: WEEK 5 R to WEEK 5 F
4.2.4 | Testing of CNN for tiny ImageNet dataset | Chirag | 2022-02-14 | 2022-03-18 | 5 | 100% | bar: WEEK 5 R to WEEK 5 F
4.2.5 | Testing of CNN for ImageNet & QR dataset | Chirag, Dhruva | 2022-03-23 | 2022-04-25 | 4 | 100% | bar: WEEK 6 M to WEEK 6 W
5 | Report Preparation
5.1 | Black Book | #NAME? | 2021-12-04 | 2022-03-08 | 1 | 100%
5.1 | PPT | Dhruva, Chirag | 2021-12-04 | 2022-03-08 | 1 | 100%
5.1 | Gantt Chart | Dhruva | 2021-12-11 | 2022-03-15 | 1 | 100% | bar: WEEK 12 M to WEEK 12 F