## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | BeSafe: IoT Based Safety Band |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY
PROJECT GUIDE |  | Asst Prof. Sonal Jain |  |  |  |  | DATE | [6 empty] | 2022-03-25
[13 empty] | 1 week=4weeks |  | 4 weeks
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Pratik, Apoorva, Priyanka | 2021-09-08 | 2022-02-01 | 1 | 100% | bar: WEEK 3 W to WEEK 6 W
1.1.1 | Research paper finalization | Pratik, Apoorva, Priyanka | 2021-11-10 | 2022-02-01 | 1 | 100% | bar: WEEK 4 F to WEEK 7 F
1.2 | Project Title | Pratik, Apoorva, Priyanka | 2021-05-10 | 2021-07-05 | 1 | 100% | bar: WEEK 1 M to WEEK 2 F
1.3 | Abstract | Apoorva | 2021-07-06 | 2021-08-10 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.4 | Objectives | Pratik | 2021-08-11 | 2021-08-18 | 1 | 100% | bar: WEEK 4 M
1.5 | Literature Review | Pratik, Priyanka | 2021-08-11 | 2021-10-01 | 1 | 100% | bar: WEEK 4 M to WEEK 5 W
1.6 | Problem Definition | Apoorva | 2021-07-05 | 2021-07-07 | 1 | 100% | bar: WEEK 3 M
1.7 | Scope | Pratik | 2021-07-05 | 2021-10-05 | 1 | 100% | bar: WEEK 3 M to WEEK 5 F
1.8 | Technology stack | Pratik | 2021-07-05 | 2021-07-15 | 1 | 100% | bar: WEEK 3 M
1.9 | Benefits for environment | Pratik | 2021-07-07 | 2021-09-07 | 1 | 100% | bar: WEEK 3 M to WEEK 4 F
1.1 | Benefits for society | Apoorva | 2021-07-07 | 2021-09-07 | 1 | 100% | bar: WEEK 3 M to WEEK 4 F
1.11 | Applications | Pratik | 2021-07-05 | 2021-07-10 | 1 | 100% | bar: WEEK 3 M
2 | Project Design
2.1 | Proposed System | Priyanka | 2021-07-18 | 2021-08-01 | 1 | 100% | bar: WEEK 3 T; WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Pratik | 2021-07-18 | 2021-08-02 | 1 | 100% | bar: WEEK 3 T; WEEK 4 F to WEEK 5 F
2.3 | Activity Diagram | Pratik, Apoorva | 2021-07-18 | 2021-08-02 | 1 | 100% | bar: WEEK 3 T
2.4 | Use Case Diagram | Pratik | 7//18/21 | 2021-08-02 | 1 | 100% | bar: WEEK 3 T
2.5 | Sequence Diagram | Priyanka | 2021-07-18 | 2021-08-02 | 1 | 100% | bar: WEEK 3 T
2.6 | Description Of Use Case | Pratik | 2021-07-19 | 2021-08-02 | 1 | 100% | bar: WEEK 3 T
2.7 | Modules | Pratik, Apoorva, Priyanka | 2021-07-23 | 2021-08-04 | 1 | 100% | bar: WEEK 3 W
2.7.1 | Application Module | Pratik | 2021-07-23 | 8/5/21. | 1 | 100% | bar: WEEK 3 W
2.7.2 | Hardware Module | Apoorva | 2021-07-18 | 2021-10-05 | 1 | 100% | bar: WEEK 3 T to WEEK 5 F
2.7.3 | App & Hardware Module | Pratik, Apoorva | 2021-07-18 | 2021-10-05 | 1 | 100% | bar: WEEK 3 T to WEEK 5 F
2.8 | Preparation Of Report | Pratik, Apoorva,Priyanka | 2021-08-05 | 2021-08-15 | 1 | 100% | bar: WEEK 3 W
3 | Project Implementation
3.1 | Application Implementation | Pratik, Apoorva, Priyanka | 2021-08-02 | 2022-02-25 | 16 | 100% | bar: WEEK 3 T to WEEK 7 M
3.2 | Hardware Implementation | Pratik, Apoorva, Priyanka | 2021-12-05 | 2022-03-05 | 12 | 100% | bar: WEEK 1 M to WEEK 7 F
3.3 | App & Hardware Integration | Pratik, Apoorva, Priyanka | 2022-03-05 | 3/25/22 | 3 | 100% | bar: WEEK 8 M
4 | Testing
4.1 | Design of Test Cases | Pratik | 8/31/21 | 2021-12-06 | 3 | 100% | bar: WEEK 3 W to WEEK 5 F
4.2.1 | Login Page Unit testing | Pratik | 2021-12-01 | 2022-01-20 | 1 | 100% | bar: WEEK 6 M
4.2.2 | Register Page Unit testing | Pratik | 2021-12-03 | 2022-01-20 | 1 | 100% | bar: WEEK 6 M
4.2.3 | Home Page Unit testing | Pratik | 2022-01-05 | 2022-01-28 | 1 | 100% | bar: WEEK 6 M
4.2.4 | Integration Testing of above pages | Pratik, Apoorva | 2022-01-28 | 2022-01-30 | 1 | 100% | bar: WEEK 6 M
4.2.5 | Database Testing | Pratik | 2021-12-01 | 2021-12-06 | 1 | 100% | bar: WEEK 6 M
4.2.6 | Machine Learning Testing | Pratik | 2022-01-28 | 2022-02-08 | 1 | 100% | bar: WEEK 6 T
4.2.7 | Integration Testing of both Functions | Pratik, Apoorva | 2022-01-28 | 2022-02-08 | 1 | 100% | bar: WEEK 6 T
4.2.8 | SOS button Integration Testing | Pratik, Apoorva | 2022-01-29 | 2022-03-10 | 1 | 100% | bar: WEEK 6 T to WEEK 6 W
4.2.9 | Compatibility Testing in other OS | Pratik, Apoorva, Priyanka | 3/20/22 | 3/31/22 | 1 | 100% | bar: WEEK 6 W to WEEK 6 R